## Summary
WellValet — Launch Readiness Summary
Auto-generated on: run date. Refer to Master Checklist for authoritative status.
By Priority
Priority | Count
Critical | 34
High | 21
Medium | 11
Low | 3
By Status
Status | Count
Not Started | 47
In Progress | 5
Blocked | 1
Done | 16
N/A | 1
By Category
Category | Count
Accounts | 4
App Identity | 4
Assets | 5
Backend | 4
Build Config | 9
Legal | 8
Monetisation | 5
Permissions | 5
QA | 6
Screenshots | 5
Store Text | 7
Submit | 4
Testing | 4
By Owner
Owner | Count
Backend | 1
Designer | 7
Prabhat | 39
Sanjeev | 23
Recommended launch order
1. Open Apple Developer + Play Console accounts (Sanjeev)
2. Draft Privacy Policy + Terms and host at wellvalet.com (Sanjeev)
3. Fill eas.json submit config with real Apple IDs (Prabhat)
4. Designer ships icon 1024, feature graphic, 8 screenshots (Designer)
5. RevenueCat + IAP wiring in trial-offer.tsx (Prabhat)
6. First EAS production build for iOS + Android (Prabhat)
7. TestFlight internal + Play internal test with 5–10 people (Prabhat + team)
8. Fix crash/UX issues found in beta
9. Fill store listings, screenshots, data safety, nutrition labels (Sanjeev)
10. Submit for Apple review + Play production (staged 10% rollout)

## Master Checklist
WellValet — Store Launch Checklist
Complete every Critical + High item before submitting to review. Sanjeev = business/legal, Prabhat = engineering.
ID | Category | Platform | Task | Details / Notes | Priority | Status | Owner
A1 | Accounts | Apple | Apple Developer Program membership | US$99/year. Already enrolled ✓ — verify membership active + payment renewed. | Critical | Done | Sanjeev
A2 | Accounts | Google | Google Play Console developer account | Organization: CruisE AnalytiX (Account ID 9194497335110928309). Android developer verification DONE ✓. | Critical | Done | Sanjeev
A3 | Accounts | Apple | App Store Connect app record created | Create app entry, get ASC App ID. | Critical | Not Started | Sanjeev
A4 | Accounts | Google | Play Console app record created | WellValet entry exists ✓. Package com.cruiseanalytix.wellvalet. Currently on Internal testing track, status 'Ready to publish'. | Critical | Done | Sanjeev
ID1 | App Identity | Both | Bundle ID / package: com.cruiseanalytix.wellvalet | Locked in app.json — do NOT change after first submission. | Critical | Done | Prabhat
ID2 | App Identity | Both | App display name: WellValet | app.json name. | Critical | Done | Prabhat
ID3 | App Identity | Both | Version 1.0.0 / buildNumber 1 | Increment before every submit. | High | Done | Prabhat
ID4 | App Identity | Both | EAS project linked | projectId 31a587a7-… + owner ecosystem-analytix. | Critical | Done | Prabhat
L1 | Legal | Both | Privacy Policy hosted publicly | Must cover camera, photos, health data (allergies), account, purchase history, AI queries, affiliate partners, analytics. URL: wellvalet.com/privacy. | Critical | Not Started | Sanjeev
L2 | Legal | Both | Terms of Service hosted publicly | URL: wellvalet.com/terms. | Critical | Not Started | Sanjeev
L3 | Legal | Both | Support email / contact URL | cruise.analytix@gmail.com or dedicated support address. | High | Done | Prabhat
L4 | Legal | Apple | Privacy Nutrition Labels filled in ASC | Declare every data type collected/linked/tracked. | Critical | Not Started | Sanjeev
L5 | Legal | Google | Data Safety form filled in Play Console | Declare all data types + purpose + encryption in transit. | Critical | Not Started | Sanjeev
L6 | Legal | Google | Content rating (IARC questionnaire) | Complete in Play Console. Health & food related — likely PEGI 3 / Everyone. | High | Not Started | Sanjeev
L7 | Legal | Apple | Age rating in App Store Connect | 4+ or 12+ based on health content questionnaire. | High | Not Started | Sanjeev
L8 | Legal | Apple | Export compliance | ITSAppUsesNonExemptEncryption = false set in Info.plist. | High | Done | Prabhat
T1 | Store Text | Both | App title (≤30 chars) | "WellValet – Wellness Scanner" (26 chars). | High | Not Started | Sanjeev
T2 | Store Text | Apple | Subtitle (≤30 chars) | Short tagline. e.g. Scan · Analyse · Improve. | High | Not Started | Sanjeev
T3 | Store Text | Google | Short description (≤80 chars) | Play Store card summary. | High | Not Started | Sanjeev
T4 | Store Text | Both | Full description (≤4000 chars) | Features, USP, target audience, CTA. | High | Not Started | Sanjeev
T5 | Store Text | Apple | Keywords (≤100 chars) | Comma-separated, iOS only. | Medium | Not Started | Sanjeev
T6 | Store Text | Apple | Promotional text (≤170 chars) | Can be edited without new build. | Low | Not Started | Sanjeev
T7 | Store Text | Both | What's New / release notes | For v1.0 — a launch note. | Medium | Not Started | Sanjeev
G1 | Assets | Apple | iOS App Icon 1024×1024 PNG (no alpha, no rounded corners) | Required for App Store listing. | Critical | Not Started | Designer
G2 | Assets | Google | Play Store icon 512×512 PNG (32-bit alpha) | Different from adaptive icon. | Critical | Not Started | Designer
G3 | Assets | Google | Feature graphic 1024×500 | Play listing header banner. | Critical | Not Started | Designer
G4 | Assets | Both | Adaptive icon (Android) foreground/background/monochrome | Already present in assets/images/. | High | Done | Prabhat
G5 | Assets | Both | Splash screen asset production-ready | assets/images/splash-icon.png — verify contrast on dark bg. | High | Done | Prabhat
S1 | Screenshots | Apple | 6.7" iPhone (1290×2796) — min 3, max 10 | Mandatory device size for App Store. | Critical | Not Started | Designer
S2 | Screenshots | Apple | 6.5" iPhone (1284×2778) OR reuse 6.7" | Optional if only 6.7 provided (Apple upscales). | Medium | Not Started | Designer
S3 | Screenshots | Google | Android phone screenshots (min 1080px shortest edge) | Min 2, max 8. | Critical | Not Started | Designer
S4 | Screenshots | Both | Screenshots cover: Scan, Beauty, AI Valet, Meal Planner, Shopping List, Family Plan, Score Ring, Onboarding | 8 shots with headline captions. | High | Not Started | Designer
S5 | Screenshots | Apple | iPad screenshots | app.json supportsTablet = false — SKIP unless enabling iPad. | N/A | N/A | Prabhat
B1 | Build Config | Both | EAS CLI installed + logged in | npm install -g eas-cli && eas login. | Critical | Not Started | Prabhat
B2 | Build Config | Both | eas.json production profile | Present ✓ — autoIncrement on iOS. | High | Done | Prabhat
B3 | Build Config | Apple | eas.json submit.production.ios values | appleTeamId = KQK3S6DD65 (MIKE SOPHIE) ✓ filled. Still need appleId email + ascAppId. | Critical | In Progress | Prabhat
B3a | Build Config | Apple | Confirm 'MIKE SOPHIE' Apple Developer account ownership | Team ID KQK3S6DD65 currently registered to MIKE SOPHIE. Confirm this is the account WellValet will launch under, or plan an app transfer. | Critical | Blocked | Sanjeev
B3b | Build Config | Apple | Apple Distribution certificate exists | Xcode currently shows Development cert only. EAS will auto-generate Distribution cert on first `eas build --profile production` for iOS. | High | Not Started | Prabhat
B4 | Build Config | Apple | Apple certs + provisioning profiles | Let EAS manage automatically (recommended). | Critical | Not Started | Prabhat
B5 | Build Config | Google | Android keystore backed up | eas credentials → download JKS. Loss = cannot update app forever. | Critical | Not Started | Prabhat
B6 | Build Config | Google | Play service account JSON | Play Console → Setup → API access → create SA → Release Manager role. Save as ./google-play-service-account.json (already gitignored, path wired in eas.json ✓). | Critical | Not Started | Prabhat
B7 | Build Config | Both | Production build passes locally / on EAS | eas build --platform ios/android --profile production. | Critical | Not Started | Prabhat
P1 | Permissions | Apple | NSCameraUsageDescription | Set ✓ — used for barcode + OCR scan. | Critical | Done | Prabhat
P2 | Permissions | Apple | NSPhotoLibraryUsageDescription | Set ✓. | High | Done | Prabhat
P3 | Permissions | Apple | NSLocationWhenInUseUsageDescription | Set ✓ (Xcode confirmed). Verify if actually used in-app; remove if not. | Medium | In Progress | Prabhat
P3a | Permissions | Apple | NSMicrophoneUsageDescription | Visible in Xcode Signing pane. Verify usage — remove if microphone is not used anywhere in code. | Medium | Not Started | Prabhat
P4 | Permissions | Google | Camera + storage permission strings | Auto-generated by Expo — verify manifest. | High | Not Started | Prabhat
IP1 | Monetisation | Apple | In-App Purchase products created in ASC | Monthly + Annual + Family SKUs matching backend plan_key. | Critical | Not Started | Sanjeev
IP2 | Monetisation | Google | In-App Products / Subscriptions in Play Console | Same SKUs. Set base plan + offers for trial. | Critical | Not Started | Sanjeev
IP3 | Monetisation | Both | RevenueCat integration in app | TODO in trial-offer.tsx — replace setPremium mock with RevenueCat. | Critical | In Progress | Prabhat
IP4 | Monetisation | Both | Tax & Banking info in both consoles | Required before paid apps/IAP go live. | Critical | Not Started | Sanjeev
IP5 | Monetisation | Apple | Sign in with Apple (if any social login) | Mandatory if Google/other social login exists. | High | Not Started | Prabhat
TT1 | Testing | Apple | TestFlight internal testing (up to 100) | No beta review. Fastest path. | High | Not Started | Prabhat
TT2 | Testing | Apple | TestFlight external testing (up to 10,000) | Requires Beta App Review (~24 hrs). | Medium | Not Started | Prabhat
TT3 | Testing | Google | Play internal testing track | Already active ✓ — build in Internal testing status 'Ready to publish' as of Jul 23 2026. Add testers via Play Console → Testing → Internal testing → Testers. | High | In Progress | Prabhat
TT4 | Testing | Google | Play closed → open testing (staged rollout) | Optional but recommended before Production. | Medium | Not Started | Prabhat
BE1 | Backend | Both | api.wellvalet.com production stable + HTTPS valid | SSL cert valid, rate limiting on, auth flow tested. | Critical | In Progress | Backend
BE2 | Backend | Both | OTA updates channel configured | runtimeVersion 1.0.0 + expo updates URL — already set ✓. | High | Done | Prabhat
BE3 | Backend | Both | Deep linking domain verified | Universal Links (iOS) + App Links (Android) if using https://wellvalet.com/ paths. | Medium | Not Started | Prabhat
BE4 | Backend | Both | Push notifications (if launching with) | APNs cert + FCM sender ID. Currently NOT in scope for v1.0? | Low | Not Started | Prabhat
Q1 | QA | Both | Emoji cleanup complete | All emojis replaced with @expo/vector-icons. | High | Done | Prabhat
Q2 | QA | Both | No console.log / debug code in production | Grep for console.log, __DEV__ leaks. | Medium | Not Started | Prabhat
Q3 | QA | Both | Crashlytics / Sentry (optional) | Recommended for prod crash tracking. | Low | Not Started | Prabhat
Q4 | QA | Both | Real-device smoke test — camera, OCR, AI Valet, IAP | Cannot be simulator-only. | Critical | Not Started | Prabhat
Q5 | QA | Both | Offline behaviour tested | OfflineBanner + graceful fallbacks. | Medium | Not Started | Prabhat
Q6 | QA | Both | Accessibility (VoiceOver + TalkBack sanity) | Icons need accessibilityLabel where they replaced emoji-text. | Medium | Not Started | Prabhat
SUB1 | Submit | Apple | eas submit --platform ios --latest | Uploads to App Store Connect. | Critical | Not Started | Prabhat
SUB2 | Submit | Google | eas submit --platform android --latest | Uploads AAB to Play Console track. | Critical | Not Started | Prabhat
SUB3 | Submit | Apple | Submit for App Review | Answer review notes: test account creds + demo family invite code. | Critical | Not Started | Sanjeev
SUB4 | Submit | Google | Submit to Production / Managed rollout | Start with 10% rollout, monitor crash-free rate. | Critical | Not Started | Sanjeev

## Apple App Store
Apple App Store — Specific Requirements
Complements the Master Checklist with store-specific policy & setup items.
Section | Item | Details
Enrolment | Apple ID with 2FA enabled | Personal Apple ID used for Developer account.
Enrolment | D-U-N-S number (Organisation only) | Free from Dun & Bradstreet. 1–5 days verification.
Enrolment | Legal entity verification | Ecosystems AnalytiX International Inc. registration docs.
ASC Setup | Bank account + Tax forms in Agreements, Tax, and Banking | Mandatory before paid apps or IAP.
ASC Setup | Users & Access — invite team members with correct roles | Admin, App Manager, Developer, Marketing.
ASC Setup | App-specific password OR ASC API key | For EAS Submit. API key preferred (safer, revocable).
App Review | Demo account credentials for reviewer | Create a permanent test user reviewer can log in with.
App Review | App Review notes | Explain barcode scanning, allergen alerts, affiliate links.
App Review | Contact info (phone + email) | Reviewer must be able to reach you within 48h.
App Review | Content rights | Confirm all product images, brand logos have rights or use public data (OpenFoodFacts etc).
Guidelines | 4.2 Minimum Functionality | Must be more than a webview. WellValet has native camera + logic ✓.
Guidelines | 5.1 Privacy — Data collection consent | Login/signup must show TOS + Privacy links.
Guidelines | 5.1.1(v) Account deletion in-app | MANDATORY. Add 'Delete Account' in profile — verify implemented.
Guidelines | 3.1.1 IAP for digital goods | Premium unlock MUST use IAP, not external Stripe/URL.
Guidelines | 1.4.1 Physical harm — Health claims | Add disclaimer: 'Not medical advice'. Present in disclaimers ✓.

## Google Play
Google Play — Specific Requirements
Complements the Master Checklist with store-specific policy & setup items.
Section | Item | Details
Enrolment | Google account with 2FA enabled | Business email preferred.
Enrolment | Developer verification (ID + address) | New Play requirement since 2023.
Enrolment | Organisation D-U-N-S if publishing as company | Required for company account since Sep 2023.
Console Setup | Merchant account (Google Payments) | Required for paid apps / IAP.
Console Setup | API access → Service account with Release Manager role | JSON key used by EAS Submit.
Console Setup | App signing by Google Play (default, recommended) | Upload key vs. app signing key — EAS handles upload key.
Policies | Target API level ≥ 34 (Android 14) by Aug 2025 | Expo SDK 51+ compiles against 34 automatically.
Policies | App bundle (.aab) only — no APK for Production | eas.json production profile builds AAB by default ✓.
Policies | 64-bit only requirement | Expo/RN handles by default.
Policies | Health apps declaration | Play Console asks about medical/wellness claims — answer honestly.
Policies | News apps declaration | No.
Policies | COVID-19 apps declaration | No.
Policies | Financial features | No — until IAP live.
Policies | Family policy compliance | If targeting under-13 → additional constraints. Target 13+.
Store Listing | App category: Health & Fitness (primary), Food & Drink (secondary) | Cannot pick 2 primaries.
Store Listing | Tags (up to 5) | Pick from Play's tag catalogue.
Store Listing | Contact details (email, phone, website) | Website: wellvalet.com.
Store Listing | External marketing opt-in | Play marketing surfaces.

## Assets Reference
Asset Sizes & Formats
Everything the designer must ship.
Asset | Size | Format | Platform | Notes
iOS App Icon | 1024×1024 | PNG, no alpha, sRGB | Apple | App Store listing
iOS Adaptive Icons | Multiple sizes | Handled by Expo | Apple | Auto-generated from icon
Play Store Icon | 512×512 | PNG, 32-bit alpha | Google | Play listing
Feature Graphic | 1024×500 | PNG or JPG | Google | Play listing header
Adaptive Icon Fg | 108×108 dp / 432×432 px | PNG | Google | app.json ✓
Adaptive Icon Bg | 108×108 dp | PNG or solid color | Google | app.json ✓
Monochrome Icon | 108×108 dp | PNG | Google | Themed icon (A13+)
iPhone 6.7" Shot | 1290×2796 | PNG or JPG | Apple | Mandatory size
iPhone 6.5" Shot | 1284×2778 | PNG or JPG | Apple | Optional if 6.7 provided
iPhone 5.5" Shot | 1242×2208 | PNG or JPG | Apple | Optional (older devices)
iPad 12.9" Shot | 2048×2732 | PNG or JPG | Apple | SKIP (iPad off)
Android Phone Shot | ≥1080 shortest side, 16:9 or 9:16 | PNG or JPG | Google | Min 2, max 8
Android Tablet Shot | 7" + 10" | PNG or JPG | Google | Optional
App Preview Video | Vertical H.264, ≤30s | MOV/MP4 | Apple | Optional but boosts conversion
Promo Video | YouTube URL | Any format on YT | Google | Optional
Splash Screen | 1284×2778 base | PNG | Both | app.json splash asset ✓

## Legal & Compliance
Legal, Privacy & Compliance
Store rejections most often happen here. Get these right.
Item | Platform | Requirement | What to declare / do | Status
Privacy Policy | Both | Public URL required. Must list ALL data collected + purpose + third parties. | Camera images (not stored server-side), account data, wellness profile (allergies — sensitive), purchase history, AI Valet queries, affiliate click IDs. | Not Started
Terms of Service | Both | Public URL. Cover subscription auto-renew, cancellation, refund policy, liability limitations. | Include disclaimer: 'WellValet is not medical advice.' | Not Started
Data Safety Form | Google | Play Console → App content → Data safety. | Declare: Personal info (email, name), Health & fitness (allergies), Purchase history, App activity (scans), Camera. Encrypted in transit = YES. | Not Started
Privacy Nutrition Labels | Apple | ASC → App Privacy → Manage. | Data types linked to user: Contact Info, Health & Fitness, Purchases, User Content, Identifiers. Purposes: App Functionality, Analytics. | Not Started
Age Rating (Apple) | Apple | Answer questionnaire in ASC. | Health/Medical treatment info → Infrequent/Mild → Rated 4+ or 12+. | Not Started
Content Rating (Google) | Google | IARC questionnaire. | Likely PEGI 3 / Everyone. | Not Started
Health disclaimer visible in-app | Both | Show 'Not medical advice' near scan results. | Already present in scan disclaimers ✓. | Done
Account deletion in-app | Both | Apple Guideline 5.1.1(v) MANDATORY. | Verify profile screen has Delete Account button + backend endpoint. | In Progress
Cookie / tracking consent | Both | If any analytics SDK (Firebase, Amplitude, etc.) is added later. | Currently none integrated. | N/A
EULA (optional) | Apple | Custom EULA or default Apple EULA. | Default works unless custom clauses needed. | N/A
GDPR readiness | Both | If EU users targeted — right to erasure, data export. | Backend endpoints for /account/delete + /account/export. | Not Started
HIPAA scope check | Both | US medical data — NOT HIPAA regulated since not a covered entity. | Wellness app, not medical provider — HIPAA not applicable. | N/A